## Dashboard
Cartridge & Cloud — QA Operational Matrix
Operational workbook v0.3.4 — S0.8 smoke-test execution pending
KPI | Value | QA scope
Test cases | 55 | Validated through | S0.7
Passed | 43 | Current QA block | S0.8
Passed with observation | 1 | Target editor | 6000.3.18f1
Pending | 11 | Repository | BLRochaGonzalez93/U012_CartridgeAndCloud
Failed | 0 | Primary environment | Windows x64 development machine
Pass rate | 80% | Next validation | Run 5 EditMode and 4 PlayMode tests
Open issues | 4

## Test_Cases
Test ID | Block | Area | Test case | Priority | Type | Automatable | Result | Evidence | Notes
QA-S0-001 | S0.1 | Toolchain | Unity Hub shows editor 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_UnityHub_EditorVersion.png | Developer confirmed
QA-S0-002 | S0.1 | Toolchain | Help > About Unity shows 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_AboutUnity.png | Present in repository
QA-S0-003 | S0.1 | Documentation | DevelopmentEnvironment_Record is complete | P2 | Review | No | PENDING | Documentation/10_Development_Records/Environment/DevelopmentEnvironment_Record.md | Deferred to S0.10
QA-S0-004 | S0.2 | Project | ProjectVersion.txt matches 6000.3.18f1 | P0 | Automated | Yes | PASS | ProjectSettings/ProjectVersion.txt | Audited on main
QA-S0-005 | S0.2 | Player Settings | Company, product and version are configured | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-006 | S0.2 | Rendering | URP is assigned and valid | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-007 | S0.2 | Rendering | Color space is Linear | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-008 | S0.2 | Serialization | Asset serialization is Force Text | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-009 | S0.2 | Compilation | Console contains zero red errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-010 | S0.3 | Packages | Required packages are installed | P0 | Review | Yes | PASS | Packages/manifest.json | AI Navigation, Input System, Localization, URP, Test Framework
QA-S0-011 | S0.3 | Packages | Required packages use non-preview versions | P0 | Review | Yes | PASS | Packages/manifest.json | No preview suffixes in required packages
QA-S0-012 | S0.3 | Packages | No unnecessary template packages remain | P2 | Review | Yes | PASS WITH OBSERVATION | Packages/manifest.json | Collab Proxy, Multiplayer Center, Visual Scripting and Timeline require decision
QA-S0-013 | S0.4 | Version control | Library, Logs and UserSettings are ignored | P0 | Manual | No | PASS | GitHub Desktop clean after Unity reopen | Confirmed
QA-S0-014 | S0.4 | Version control | .csproj and .slnx are ignored | P1 | Manual | No | PASS | .gitignore | Confirmed
QA-S0-015 | S0.4 | Version control | .vsconfig is tracked | P2 | Review | Yes | PASS | Repository root | Confirmed
QA-S0-016 | S0.4 | Version control | .gitattributes exists and classifies text/binary assets | P1 | Review | Yes | PASS | .gitattributes | Confirmed
QA-S0-017 | S0.4 | Repository | Unity open/close leaves GitHub Desktop clean | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-018 | S0.5 | Structure | Assets/_Project hierarchy exists | P0 | Review | Yes | PASS | Assets/_Project | Committed
QA-S0-019 | S0.5 | Documentation | Official baseline is stored outside Assets | P0 | Review | Yes | PASS | Documentation/00_Official_Baseline/v0.3 | Committed
QA-S0-020 | S0.5 | Documentation | Official baseline contains the expected 61 files | P1 | Review | Yes | PASS | Document_Location_Map_v0.3.csv | Confirmed during integration
QA-S0-021 | S0.5 | Documentation | RAR source is not included in repository | P1 | Review | Yes | PASS | Repository audit | Confirmed
QA-S0-022 | S0.6 | Assemblies | Six asmdef files exist in exact paths | P0 | Review | Yes | PASS | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Audited
QA-S0-023 | S0.6 | Assemblies | Domain has no references and No Engine References | P0 | Review | Yes | PASS | Domain asmdef | Developer confirmed
QA-S0-024 | S0.6 | Assemblies | Application references only Domain and has No Engine References | P0 | Review | Yes | PASS | Application asmdef | Developer confirmed
QA-S0-025 | S0.6 | Assemblies | Infrastructure and Presentation do not reference each other | P0 | Review | Yes | PASS | Infrastructure/Presentation asmdefs | Audited
QA-S0-026 | S0.6 | Assemblies | EditMode targets Editor and PlayMode targets Any Platform | P1 | Review | Yes | PASS | Test asmdefs | Audited
QA-S0-027 | S0.6 | Compilation | Assemblies compile without cyclic or duplicate errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-028 | S0.6 | Testing | Test Runner opens successfully | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0D-001 | S0.6D | Documentation | Operational production workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-002 | S0.6D | Documentation | Operational QA workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-003 | S0.6D | Documentation | Operational traceability workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-004 | S0.6D | Documentation | S0.5 and S0.6 records show closed PASS state | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-005 | S0.6D | Repository | Commit and push leave GitHub Desktop clean | P0 | Manual | No | PASS | Developer confirmation | S0.6D confirmed
QA-S07-001 | S0.7 | Scenes | Four scene assets exist at exact paths | P0 | Review | Yes | PASS | Assets/_Project/Scenes | Developer-confirmed; repository and Scene List audited
QA-S07-002 | S0.7 | Scenes | Every scene asset has a Unity-generated .meta file | P0 | Review | Yes | PASS | Assets/_Project/Scenes | Developer-confirmed; repository and Scene List audited
QA-S07-003 | S0.7 | Bootstrap | Bootstrap hierarchy is empty | P0 | Manual | No | PASS | Evidence/S0.7_BootstrapHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-004 | S0.7 | MainMenu | MainMenu contains only Main Camera and Directional Light | P1 | Manual | No | PASS | Evidence/S0.7_MainMenuHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-005 | S0.7 | Store | Store contains only Main Camera and Directional Light | P0 | Manual | No | PASS | Evidence/S0.7_StoreHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-006 | S0.7 | TestLab | TestLab contains only Main Camera and Directional Light | P1 | Manual | No | PASS | Evidence/S0.7_TestLabHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-007 | S0.7 | Cleanup | SampleScene is removed from project and Scene List | P1 | Review | Yes | PASS | Repository / Scene List | Scene asset removed; stale disabled Scene List entry detected after initial commit and removed in 6416ca107509
QA-S07-008 | S0.7 | Build Profiles | Global Scene List order is Bootstrap, MainMenu, Store, TestLab | P0 | Manual | No | PASS | Evidence/S0.7_SceneList.png | Final global order verified: Bootstrap, MainMenu, Store, TestLab
QA-S07-009 | S0.7 | Build Profiles | All four global Scene List entries are enabled | P0 | Manual | No | PASS | Evidence/S0.7_SceneList.png | Developer-confirmed; repository and Scene List audited
QA-S07-010 | S0.7 | Play Mode | Each scene enters and exits Play Mode without red errors | P0 | Manual | No | PASS | Evidence/S0.7_ConsoleClean.png | Developer-confirmed; repository and Scene List audited
QA-S07-011 | S0.7 | Persistence | Scene List and scene assets survive Unity restart | P0 | Manual | No | PASS | Developer validation | Developer-confirmed; repository and Scene List audited
QA-S07-012 | S0.7 | Repository | Commit and push leave GitHub Desktop clean | P0 | Manual | No | PASS | Commits 72af6f82cc44; 6416ca107509 | Developer-confirmed; repository and Scene List audited
QA-S08-001 | S0.8 | Compilation | Three smoke-test scripts import and compile without errors | P0 | Manual | No | PENDING | Evidence/S0.8_TestScripts.png | Unity must generate three .meta files
QA-S08-002 | S0.8 | Test discovery | Test Runner discovers exactly five EditMode tests | P0 | Manual | No | PENDING | Evidence/S0.8_EditMode_Pass.png | No missing or duplicate tests
QA-S08-003 | S0.8 | Assemblies | Production Assembly Definition dependency graph smoke test passes | P0 | Automated | Yes | PENDING | Test Runner | Protects Domain/Application boundaries
QA-S08-004 | S0.8 | Assemblies | Test Assembly Definition platform and reference smoke test passes | P0 | Automated | Yes | PENDING | Test Runner | EditMode Editor-only; PlayMode Any Platform
QA-S08-005 | S0.8 | Scenes | Scene assets, global Scene List and build indexes smoke tests pass | P0 | Automated | Yes | PENDING | Test Runner | Three EditMode tests
QA-S08-006 | S0.8 | EditMode | Complete EditMode suite returns 5 PASS and 0 FAIL | P0 | Manual | No | PENDING | Evidence/S0.8_EditMode_Pass.png | Run All
QA-S08-007 | S0.8 | Test discovery | Test Runner discovers exactly four PlayMode tests | P0 | Manual | No | PENDING | Evidence/S0.8_PlayMode_Pass.png | One test per scene
QA-S08-008 | S0.8 | PlayMode | Bootstrap loads and contains zero root GameObjects | P0 | Automated | Yes | PENDING | Test Runner | Scene index 0
QA-S08-009 | S0.8 | PlayMode | MainMenu, Store and TestLab load with approved camera/light roots | P0 | Automated | Yes | PENDING | Test Runner | Three UnityTests
QA-S08-010 | S0.8 | Regression | All nine tests pass again after Unity restart with a clean Console | P0 | Manual | No | PENDING | Evidence/S0.8_ConsoleClean.png | Required before commit

## Test_Runs
Run ID | Date | Block | Environment | Scope | Result | Executed by | Evidence / Notes
RUN-S0-001 | 2026-06-21 | S0.1 | Unity 6000.3.18f1 / Windows | Toolchain and editor version | PASS | Blas Luis Rocha González | Two screenshots stored in Evidence
RUN-S0-002 | 2026-06-21 | S0.2 | Unity 6000.3.18f1 / URP | Project settings, URP and clean console | PASS | Blas Luis Rocha González | Developer-confirmed manual run
RUN-S0-003 | 2026-06-21 | S0.3 | Unity Package Manager | Required package baseline | PASS WITH OBSERVATION | Blas Luis Rocha González | Unused template packages remain for review
RUN-S0-004 | 2026-06-21 | S0.4 | GitHub Desktop / main | Ignore rules and clean repository state | PASS | Blas Luis Rocha González | Unity open/close produced no changes
RUN-S0-005 | 2026-06-21 | S0.5 | Unity / repository | Project and documentation structure | PASS | Blas Luis Rocha González | User confirmed all DoD items
RUN-S0-006 | 2026-06-21 | S0.6 | Unity / Test Runner | Assembly graph and compilation | PASS | Blas Luis Rocha González | User confirmed no errors
RUN-S0D-001 | 2026-06-21 | S0.6D | Repository / office suite | Documentation tracking sync | PASS | Blas Luis Rocha González | Commit 31a77be; developer confirmed
RUN-S07-001 | 2026-06-22 | S0.7 | Unity 6000.3.18f1 / Windows | Scene baseline, global Scene List and clean Play Mode | PASS | Blas Luis Rocha González | Scene baseline commit 72af6f82cc44; stale Scene List entry fixed in 6416ca107509; developer confirmed clean restart and repository state
RUN-S08-001 | 2026-06-22 | S0.8 | Unity 6000.3.18f1 / Test Framework 1.6.0 | Five EditMode and four PlayMode smoke tests | PENDING | Blas Luis Rocha González | Execute after package integration

## Issues
Issue ID | Block | Severity | Area | Description | Recommended action | Status | Target
ISS-S0-001 | S0.1 | Low | Documentation | DevelopmentEnvironment_Record remains incomplete | Complete manually before Sprint 0 closure | Open | S0.10
ISS-S0-002 | S0.3 | Medium | Packages | Template includes Collab Proxy, Multiplayer Center and Visual Scripting | Review and remove through Package Manager with regression test | Open | Before S0.7 or S0.10
ISS-S0-003 | S0.3 | Low | Packages | Timeline is installed without a current requirement | Keep only if a near-term use is documented | Open | S0.10
ISS-S0-004 | S0.5 | Medium | Documentation | S0.5 document previously showed pending state | Resolved by S0.6D operational sync | Closed | S0.6D
ISS-S0-005 | S0.6 | Medium | Documentation | S0.6 validation checklist was previously unchecked | Resolved by S0.6D operational sync | Closed | S0.6D
ISS-S0-006 | S0.6D | High | Governance | Operational Excel and traceability were absent | Resolved by commit 31a77be | Closed | S0.6D
ISS-S07-001 | S0.7 | High | Build | Initial Scene List retained a disabled stale SampleScene reference | Removed through Build Profiles and published in 6416ca107509 | Closed | S0.7
ISS-S07-002 | S0.7 | Medium | Repository | Scene or meta files could be copied outside Unity | Scenes and Unity-generated metadata published in 72af6f82cc44 | Closed | S0.7
ISS-S08-001 | S0.8 | High | Testing | Smoke-test compilation, discovery or execution can fail | Capture the complete Console/Test Runner result and fix the cause without weakening tests | Open | S0.8

## Evidence
Evidence ID | Block | Type | Path / Reference | Status | Supports
EV-S0-001 | S0.1 | Screenshot | Evidence/S0.1_UnityHub_EditorVersion.png | Available | QA-S0-001
EV-S0-002 | S0.1 | Screenshot | Evidence/S0.1_AboutUnity.png | Available | QA-S0-002
EV-S0-003 | S0.2 | File | ProjectSettings/ProjectVersion.txt | Available | QA-S0-004
EV-S0-004 | S0.3 | File | Packages/manifest.json | Available | QA-S0-010; QA-S0-011; QA-S0-012
EV-S0-005 | S0.3 | File | Packages/packages-lock.json | Available | Package restoration
EV-S0-006 | S0.4 | File | .gitignore | Available | QA-S0-013; QA-S0-014
EV-S0-007 | S0.4 | File | .gitattributes | Available | QA-S0-016
EV-S0-008 | S0.5 | Commit | 1cc30ad69a2c093a8e1e0686451302689eb632bb | Available | QA-S0-018 to QA-S0-021
EV-S0-009 | S0.6 | Commit | 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Available | QA-S0-022 to QA-S0-028
EV-S0D-001 | S0.6D | Commit | 31a77be358a3b8e9268cd69abb02a1f52d429fbd | Available | QA-S0D-001 to QA-S0D-005
EV-S07-001 | S0.7 | Screenshot | Evidence/S0.7_SceneAssets.png | Available | QA-S07-001; QA-S07-002; QA-S07-007
EV-S07-002 | S0.7 | Screenshot | Evidence/S0.7_SceneList.png | Available | QA-S07-008; QA-S07-009
EV-S07-003 | S0.7 | Screenshot | Evidence/S0.7_BootstrapHierarchy.png | Available | QA-S07-003
EV-S07-004 | S0.7 | Screenshot | Evidence/S0.7_MainMenuHierarchy.png | Available | QA-S07-004
EV-S07-005 | S0.7 | Screenshot | Evidence/S0.7_StoreHierarchy.png | Available | QA-S07-005
EV-S07-006 | S0.7 | Screenshot | Evidence/S0.7_TestLabHierarchy.png | Available | QA-S07-006
EV-S07-007 | S0.7 | Screenshot | Evidence/S0.7_ConsoleClean.png | Available | QA-S07-010
EV-S07-008 | S0.7 | Commit | 72af6f82cc4458c716d751f5846075bfe47aa093 | Available | QA-S07-001 to QA-S07-012
EV-S07-009 | S0.7 | Commit | 6416ca107509dd81428575ff9400215022bc7610 | Available | QA-S07-007; QA-S07-008
EV-S08-001 | S0.8 | Screenshot | Evidence/S0.8_TestScripts.png | Pending | QA-S08-001
EV-S08-002 | S0.8 | Screenshot | Evidence/S0.8_EditMode_Pass.png | Pending | QA-S08-002 to QA-S08-006
EV-S08-003 | S0.8 | Screenshot | Evidence/S0.8_PlayMode_Pass.png | Pending | QA-S08-007 to QA-S08-009
EV-S08-004 | S0.8 | Screenshot | Evidence/S0.8_ConsoleClean.png | Pending | QA-S08-010

## Regression_Checklist
Regression ID | Trigger | Check | Priority | Status | Notes
REG-S0-001 | Any package change | Unity opens without package resolution errors | P0 | Pending | Run after package removal
REG-S0-002 | Any package change | Console remains free of red errors | P0 | Pending | Run after package removal
REG-S0-003 | Any package change | All six asmdefs compile | P0 | Pending | Run after package removal
REG-S0-004 | Documentation sync | GitHub Desktop ignores generated Unity files | P0 | PASS | Developer confirmed S0.6D
REG-S0-005 | Documentation sync | Operational workbooks open without repair prompts | P0 | PASS | Developer confirmed S0.6D
REG-S0-006 | Documentation sync | Official baseline files remain unmodified | P0 | PASS | Commit 31a77be only changed Development_Records
REG-S07-001 | Scene creation | All six assemblies continue compiling | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-002 | Scene List change | Unity opens without missing scene references | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-003 | Scene cleanup | URP settings and template assets remain valid | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-004 | Commit | GitHub Desktop excludes generated caches | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S08-001 | Test import | The six existing asmdefs remain unchanged | P0 | Pending | Compare GitHub Desktop
REG-S08-002 | EditMode run | Scene assets and global order remain unchanged | P0 | Pending | Automated checks
REG-S08-003 | PlayMode run | All scenes load without errors or unexpected roots | P0 | Pending | Four UnityTests
REG-S08-004 | Unity restart | The complete suite passes a second time | P0 | Pending | Required before commit

## References
Reference | Purpose | URL | Accessed
Unity Test Framework manual | EditMode and PlayMode test execution | https://docs.unity.cn/6000.0/Documentation/Manual/testing-editortestsrunner.html | 2026-06-22
PlayMode tests | PlayMode assembly and execution behavior | https://docs.unity.cn/Packages/com.unity.test-framework@1.4/manual/course/play-mode-tests.html | 2026-06-22
SceneManager.LoadSceneAsync | Asynchronous scene loading used by smoke tests | https://docs.unity3d.com/ScriptReference/SceneManagement.SceneManager.LoadSceneAsync.html | 2026-06-22
Project repository | Implementation baseline | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud | 2026-06-22