## Dashboard
Cartridge & Cloud - QA Matrix v0.5
KPI | Value
EditMode baseline | 127
PlayMode baseline | 41
Full baseline | 168
Known S0/S1 defects | 0
Last validated version | 0.0.6
Next QA focus | Sprint 6 inventory invariants

## Test_Suites
Area | Mode | Current coverage | Baseline result | Regression trigger | Owner
Foundation | Edit/Play | Project and scenes | PASS | Any setup change | VRM Games
Scene Flow | Play | Bootstrap/MainMenu/Store | PASS | Navigation change | VRM Games
Save Skeleton | Edit | IDs/snapshot/contracts | PASS | Data change | VRM Games
Input Contexts | Edit/Play | UI/Gameplay routing | PASS | Input map change | VRM Games
Movement | Edit/Play | Planar movement and click ray | PASS | Player change | VRM Games
Camera | Edit/Play | Orbit/zoom constraints | PASS | Camera change | VRM Games
Grid | Edit | Coordinates/footprints/rotation | PASS | Grid change | VRM Games
Placement | Edit/Play | Preview/occupancy/removal | PASS | Placement change | VRM Games
Store Shell | Play/Manual | Dimensions/player/flow | PASS | Scene change | VRM Games
Access | Edit/Play | Entrance/anchors/BFS | PASS | Access change | VRM Games
Build | Manual | Windows x64 external run | PASS | Phase gate | VRM Games
Inventory | Edit | Planned S6 coverage | PLANNED | Sprint 6 | VRM Games

## Acceptance
ID | Sprint | Criterion | Result | Evidence
AC-00 | 0 | Foundation compiles and builds | PASS | 9/9
AC-01 | 1 | Bootstrap/MainMenu/Store flow | PASS | 14/14 + external
AC-02 | 2 | Versioned save skeleton | PASS | 27/27
AC-03 | 3 | Movement/camera/input contexts | PASS | 67/67 + build
AC-04 | 4 | Grid and placement foundation | PASS | 118/118 + build
AC-05 | 5 | Store shell and access integration | PASS | 168/168 + build
AC-06 | 6 | Product definitions and IDs | PLANNED
AC-07 | 6 | Container quantities never negative | PLANNED
AC-08 | 6 | Atomic transfer conserves units | PLANNED
AC-09 | 6 | Capacity errors do not partially mutate | PLANNED

## Regression
ID | Scenario | Expected | Current | Run when
RG-01 | Bootstrap to MainMenu | One ApplicationRoot | PASS | Every full regression
RG-02 | MainMenu to Store and return | Correct contexts | PASS | Scene/UI changes
RG-03 | Click-to-move | Moves outside construction | PASS | Input/player changes
RG-04 | Orbit and zoom | Stable constraints | PASS | Camera changes
RG-05 | Placement bounds/overlap | Invalid is red/rejected | PASS | Grid/placement changes
RG-06 | Access reserve/anchors | Route preserved | PASS | Store/access changes
RG-07 | Remove placement | Cells/routes restored | PASS | Placement changes
RG-08 | TestLab placement | No Store access rules | PASS | Placement changes
RG-09 | Store empty baseline | No placed objects | PASS | Scene installer
RG-10 | Windows external run | Flow and Quit | PASS | Phase gate
RG-11 | Inventory conservation | No unit loss/duplication | PLANNED | Sprint 6
RG-12 | Save migration | Non-destructive | PLANNED | Sprint 14

## Build_Gates
Gate | Sprint | Platform | Type | Result | Evidence
Foundation Build002 | 0 | Windows x64 | Development | PASS | External execution
Scene flow build | 1 | Windows x64 | Development | PASS | Flow and Quit
Movement/camera gate | 3 | Windows x64 | Development | PASS | Control/camera
Placement gate | 4 | Windows x64 | Development | PASS | TestLab placement
Store foundation gate | 5 | Windows x64 | Development | PASS | Store construction/access
Vertical slice build | 17 | Windows x64 | Internal | PLANNED | H6