## Dashboard
Cartridge & Cloud — QA Operational Matrix
Operational workbook v0.3.1 — Sprint 0 infrastructure and documentation validation
KPI | Value | QA scope
Test cases | 33 | Validated through | S0.6
Passed | 26 | Current QA block | S0.6D
Passed with observation | 1 | Target editor | 6000.3.18f1
Pending | 6 | Repository | BLRochaGonzalez93/U012_CartridgeAndCloud
Failed | 0 | Primary environment | Windows x64 development machine
Pass rate | 81.82% | Next validation | S0.7 scenes and Scene List
Open issues | 3

## Test_Cases
Test ID | Block | Area | Test case | Priority | Type | Automatable | Result | Evidence | Notes
QA-S0-001 | S0.1 | Toolchain | Unity Hub shows editor 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_UnityHub_EditorVersion.png | Developer confirmed
QA-S0-002 | S0.1 | Toolchain | Help > About Unity shows 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_AboutUnity.png | Present in repository
QA-S0-003 | S0.1 | Documentation | DevelopmentEnvironment_Record is complete | P2 | Review | No | PENDING | Documentation/10_Development_Records/Environment/DevelopmentEnvironment_Record.md | Deferred to S0.10
QA-S0-004 | S0.2 | Project | ProjectVersion.txt matches 6000.3.18f1 | P0 | Automated | Yes | PASS | ProjectSettings/ProjectVersion.txt | Audited on main
QA-S0-005 | S0.2 | Player Settings | Company, product and version are configured | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-006 | S0.2 | Rendering | URP is assigned and valid | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-007 | S0.2 | Rendering | Color space is Linear | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-008 | S0.2 | Serialization | Asset serialization is Force Text | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-009 | S0.2 | Compilation | Console contains zero red errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-010 | S0.3 | Packages | Required packages are installed | P0 | Review | Yes | PASS | Packages/manifest.json | AI Navigation, Input System, Localization, URP, Test Framework
QA-S0-011 | S0.3 | Packages | Required packages use non-preview versions | P0 | Review | Yes | PASS | Packages/manifest.json | No preview suffixes in required packages
QA-S0-012 | S0.3 | Packages | No unnecessary template packages remain | P2 | Review | Yes | PASS WITH OBSERVATION | Packages/manifest.json | Collab Proxy, Multiplayer Center, Visual Scripting and Timeline require decision
QA-S0-013 | S0.4 | Version control | Library, Logs and UserSettings are ignored | P0 | Manual | No | PASS | GitHub Desktop clean after Unity reopen | Confirmed
QA-S0-014 | S0.4 | Version control | .csproj and .slnx are ignored | P1 | Manual | No | PASS | .gitignore | Confirmed
QA-S0-015 | S0.4 | Version control | .vsconfig is tracked | P2 | Review | Yes | PASS | Repository root | Confirmed
QA-S0-016 | S0.4 | Version control | .gitattributes exists and classifies text/binary assets | P1 | Review | Yes | PASS | .gitattributes | Confirmed
QA-S0-017 | S0.4 | Repository | Unity open/close leaves GitHub Desktop clean | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-018 | S0.5 | Structure | Assets/_Project hierarchy exists | P0 | Review | Yes | PASS | Assets/_Project | Committed
QA-S0-019 | S0.5 | Documentation | Official baseline is stored outside Assets | P0 | Review | Yes | PASS | Documentation/00_Official_Baseline/v0.3 | Committed
QA-S0-020 | S0.5 | Documentation | Official baseline contains the expected 61 files | P1 | Review | Yes | PASS | Document_Location_Map_v0.3.csv | Confirmed during integration
QA-S0-021 | S0.5 | Documentation | RAR source is not included in repository | P1 | Review | Yes | PASS | Repository audit | Confirmed
QA-S0-022 | S0.6 | Assemblies | Six asmdef files exist in exact paths | P0 | Review | Yes | PASS | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Audited
QA-S0-023 | S0.6 | Assemblies | Domain has no references and No Engine References | P0 | Review | Yes | PASS | Domain asmdef | Developer confirmed
QA-S0-024 | S0.6 | Assemblies | Application references only Domain and has No Engine References | P0 | Review | Yes | PASS | Application asmdef | Developer confirmed
QA-S0-025 | S0.6 | Assemblies | Infrastructure and Presentation do not reference each other | P0 | Review | Yes | PASS | Infrastructure/Presentation asmdefs | Audited
QA-S0-026 | S0.6 | Assemblies | EditMode targets Editor and PlayMode targets Any Platform | P1 | Review | Yes | PASS | Test asmdefs | Audited
QA-S0-027 | S0.6 | Compilation | Assemblies compile without cyclic or duplicate errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-028 | S0.6 | Testing | Test Runner opens successfully | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0D-001 | S0.6D | Documentation | Operational production workbook exists | P0 | Review | Yes | PENDING | Production_Tracking folder | Validate after extraction
QA-S0D-002 | S0.6D | Documentation | Operational QA workbook exists | P0 | Review | Yes | PENDING | Production_Tracking folder | Validate after extraction
QA-S0D-003 | S0.6D | Documentation | Operational traceability workbook exists | P0 | Review | Yes | PENDING | Production_Tracking folder | Validate after extraction
QA-S0D-004 | S0.6D | Documentation | S0.5 and S0.6 records show closed PASS state | P0 | Review | Yes | PENDING | Sprint_00 documents | Validate after overwrite
QA-S0D-005 | S0.6D | Repository | Commit and push leave GitHub Desktop clean | P0 | Manual | No | PENDING | GitHub Desktop | Final S0.6D validation

## Test_Runs
Run ID | Date | Block | Environment | Scope | Result | Executed by | Evidence / Notes
RUN-S0-001 | 2026-06-21 | S0.1 | Unity 6000.3.18f1 / Windows | Toolchain and editor version | PASS | Blas Luis Rocha González | Two screenshots stored in Evidence
RUN-S0-002 | 2026-06-21 | S0.2 | Unity 6000.3.18f1 / URP | Project settings, URP and clean console | PASS | Blas Luis Rocha González | Developer-confirmed manual run
RUN-S0-003 | 2026-06-21 | S0.3 | Unity Package Manager | Required package baseline | PASS WITH OBSERVATION | Blas Luis Rocha González | Unused template packages remain for review
RUN-S0-004 | 2026-06-21 | S0.4 | GitHub Desktop / main | Ignore rules and clean repository state | PASS | Blas Luis Rocha González | Unity open/close produced no changes
RUN-S0-005 | 2026-06-21 | S0.5 | Unity / repository | Project and documentation structure | PASS | Blas Luis Rocha González | User confirmed all DoD items
RUN-S0-006 | 2026-06-21 | S0.6 | Unity / Test Runner | Assembly graph and compilation | PASS | Blas Luis Rocha González | User confirmed no errors
RUN-S0D-001 | 2026-06-21 | S0.6D | Repository / office suite | Documentation tracking sync | PENDING | Blas Luis Rocha González | Complete after integrating this package

## Issues
Issue ID | Block | Severity | Area | Description | Recommended action | Status | Target
ISS-S0-001 | S0.1 | Low | Documentation | DevelopmentEnvironment_Record remains incomplete | Complete manually before Sprint 0 closure | Open | S0.10
ISS-S0-002 | S0.3 | Medium | Packages | Template includes Collab Proxy, Multiplayer Center and Visual Scripting | Review and remove through Package Manager with regression test | Open | Before S0.7 or S0.10
ISS-S0-003 | S0.3 | Low | Packages | Timeline is installed without a current requirement | Keep only if a near-term use is documented | Open | S0.10
ISS-S0-004 | S0.5 | Medium | Documentation | S0.5 document still shows pending state | Replace with S0.6D closed version | In progress | S0.6D
ISS-S0-005 | S0.6 | Medium | Documentation | S0.6 validation checklist remains unchecked | Replace with completed checklist | In progress | S0.6D
ISS-S0-006 | S0.6D | High | Governance | Operational Excel and traceability were absent | Integrate S0.6D package and commit | In progress | S0.6D

## Evidence
Evidence ID | Block | Type | Path / Reference | Status | Supports
EV-S0-001 | S0.1 | Screenshot | Evidence/S0.1_UnityHub_EditorVersion.png | Available | QA-S0-001
EV-S0-002 | S0.1 | Screenshot | Evidence/S0.1_AboutUnity.png | Available | QA-S0-002
EV-S0-003 | S0.2 | File | ProjectSettings/ProjectVersion.txt | Available | QA-S0-004
EV-S0-004 | S0.3 | File | Packages/manifest.json | Available | QA-S0-010; QA-S0-011; QA-S0-012
EV-S0-005 | S0.3 | File | Packages/packages-lock.json | Available | Package restoration
EV-S0-006 | S0.4 | File | .gitignore | Available | QA-S0-013; QA-S0-014
EV-S0-007 | S0.4 | File | .gitattributes | Available | QA-S0-016
EV-S0-008 | S0.5 | Commit | 1cc30ad69a2c093a8e1e0686451302689eb632bb | Available | QA-S0-018 to QA-S0-021
EV-S0-009 | S0.6 | Commit | 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Available | QA-S0-022 to QA-S0-028
EV-S0D-001 | S0.6D | Package | CartridgeAndCloud_Sprint0_S0.6D_DocumentationSync_v001.zip | Pending integration | QA-S0D-001 to QA-S0D-005

## Regression_Checklist
Regression ID | Trigger | Check | Priority | Status | Notes
REG-S0-001 | Any package change | Unity opens without package resolution errors | P0 | Pending | Run after package removal
REG-S0-002 | Any package change | Console remains free of red errors | P0 | Pending | Run after package removal
REG-S0-003 | Any package change | All six asmdefs compile | P0 | Pending | Run after package removal
REG-S0-004 | Documentation sync | GitHub Desktop ignores generated Unity files | P0 | Pending | Run after package extraction
REG-S0-005 | Documentation sync | Operational workbooks open without repair prompts | P0 | Pending | Run locally in Excel/LibreOffice
REG-S0-006 | Documentation sync | Official baseline files remain unmodified | P0 | Pending | Review GitHub Desktop file list