## Dashboard
Cartridge & Cloud — QA Operational Matrix
Official baseline v0.4 - Sprint 0 QA closed
KPI | Value | QA scope
Test cases | 77 | Validated through: Sprint 0 | Sprint 0
Passed | 74 | Current QA block: Closed / PASS | Closed / PASS
Passed with observation | 3 | Target editor: 6000.3.18f1 | 6000.3.18f1
Pending | 0 | Repository: BLRochaGonzalez93/U012_CartridgeAndCloud | BLRochaGonzalez93/U012_CartridgeAndCloud
Failed | 0 | Environment: Windows x64 development machine | Windows x64 development machine
Pass rate | 100% | Next validation: Next sprint acceptance criteria | Next sprint acceptance criteria
Open issues | 0

## Test_Cases
Test ID | Block | Area | Test case | Priority | Type | Automatable | Result | Evidence | Notes
QA-S0-001 | S0.1 | Toolchain | Unity Hub shows editor 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_UnityHub_EditorVersion.png | Developer confirmed
QA-S0-002 | S0.1 | Toolchain | Help > About Unity shows 6000.3.18f1 | P0 | Manual | No | PASS | Evidence/S0.1_AboutUnity.png | Present in repository
QA-S0-003 | S0.1 | Documentation | DevelopmentEnvironment_Record is complete | P2 | Review | No | PASS | Documentation/10_Development_Records/Environment/DevelopmentEnvironment_Record.md | Completed in Sprint 0 closure baseline
QA-S0-004 | S0.2 | Project | ProjectVersion.txt matches 6000.3.18f1 | P0 | Automated | Yes | PASS | ProjectSettings/ProjectVersion.txt | Audited on main
QA-S0-005 | S0.2 | Player Settings | Company, product and version are configured | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-006 | S0.2 | Rendering | URP is assigned and valid | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-007 | S0.2 | Rendering | Color space is Linear | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-008 | S0.2 | Serialization | Asset serialization is Force Text | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-009 | S0.2 | Compilation | Console contains zero red errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-010 | S0.3 | Packages | Required packages are installed | P0 | Review | Yes | PASS | Packages/manifest.json | AI Navigation, Input System, Localization, URP, Test Framework
QA-S0-011 | S0.3 | Packages | Required packages use non-preview versions | P0 | Review | Yes | PASS | Packages/manifest.json | No preview suffixes in required packages
QA-S0-012 | S0.3 | Packages | No unnecessary template packages remain | P2 | Review | Yes | PASS WITH OBSERVATION | Packages/manifest.json | Collab Proxy, Multiplayer Center, Visual Scripting and Timeline require decision
QA-S0-013 | S0.4 | Version control | Library, Logs and UserSettings are ignored | P0 | Manual | No | PASS | GitHub Desktop clean after Unity reopen | Confirmed
QA-S0-014 | S0.4 | Version control | .csproj and .slnx are ignored | P1 | Manual | No | PASS | .gitignore | Confirmed
QA-S0-015 | S0.4 | Version control | .vsconfig is tracked | P2 | Review | Yes | PASS | Repository root | Confirmed
QA-S0-016 | S0.4 | Version control | .gitattributes exists and classifies text/binary assets | P1 | Review | Yes | PASS | .gitattributes | Confirmed
QA-S0-017 | S0.4 | Repository | Unity open/close leaves GitHub Desktop clean | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-018 | S0.5 | Structure | Assets/_Project hierarchy exists | P0 | Review | Yes | PASS | Assets/_Project | Committed
QA-S0-019 | S0.5 | Documentation | Official baseline is stored outside Assets | P0 | Review | Yes | PASS | Documentation/00_Official_Baseline/v0.3 | Committed
QA-S0-020 | S0.5 | Documentation | Official baseline contains the expected 61 files | P1 | Review | Yes | PASS | Document_Location_Map_v0.3.csv | Confirmed during integration
QA-S0-021 | S0.5 | Documentation | RAR source is not included in repository | P1 | Review | Yes | PASS | Repository audit | Confirmed
QA-S0-022 | S0.6 | Assemblies | Six asmdef files exist in exact paths | P0 | Review | Yes | PASS | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Audited
QA-S0-023 | S0.6 | Assemblies | Domain has no references and No Engine References | P0 | Review | Yes | PASS | Domain asmdef | Developer confirmed
QA-S0-024 | S0.6 | Assemblies | Application references only Domain and has No Engine References | P0 | Review | Yes | PASS | Application asmdef | Developer confirmed
QA-S0-025 | S0.6 | Assemblies | Infrastructure and Presentation do not reference each other | P0 | Review | Yes | PASS | Infrastructure/Presentation asmdefs | Audited
QA-S0-026 | S0.6 | Assemblies | EditMode targets Editor and PlayMode targets Any Platform | P1 | Review | Yes | PASS | Test asmdefs | Audited
QA-S0-027 | S0.6 | Compilation | Assemblies compile without cyclic or duplicate errors | P0 | Manual | No | PASS | Developer validation | Confirmed
QA-S0-028 | S0.6 | Testing | Test Runner opens successfully | P1 | Manual | No | PASS | Developer validation | Confirmed
QA-S0D-001 | S0.6D | Documentation | Operational production workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-002 | S0.6D | Documentation | Operational QA workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-003 | S0.6D | Documentation | Operational traceability workbook exists | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-004 | S0.6D | Documentation | S0.5 and S0.6 records show closed PASS state | P0 | Review | Yes | PASS | Commit 31a77be | Published on main
QA-S0D-005 | S0.6D | Repository | Commit and push leave GitHub Desktop clean | P0 | Manual | No | PASS | Developer confirmation | S0.6D confirmed
QA-S07-001 | S0.7 | Scenes | Four scene assets exist at exact paths | P0 | Review | Yes | PASS | Assets/_Project/Scenes | Developer-confirmed; repository and Scene List audited
QA-S07-002 | S0.7 | Scenes | Every scene asset has a Unity-generated .meta file | P0 | Review | Yes | PASS | Assets/_Project/Scenes | Developer-confirmed; repository and Scene List audited
QA-S07-003 | S0.7 | Bootstrap | Bootstrap hierarchy is empty | P0 | Manual | No | PASS | Evidence/S0.7_BootstrapHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-004 | S0.7 | MainMenu | MainMenu contains only Main Camera and Directional Light | P1 | Manual | No | PASS | Evidence/S0.7_MainMenuHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-005 | S0.7 | Store | Store contains only Main Camera and Directional Light | P0 | Manual | No | PASS | Evidence/S0.7_StoreHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-006 | S0.7 | TestLab | TestLab contains only Main Camera and Directional Light | P1 | Manual | No | PASS | Evidence/S0.7_TestLabHierarchy.png | Developer-confirmed; repository and Scene List audited
QA-S07-007 | S0.7 | Cleanup | SampleScene is removed from project and Scene List | P1 | Review | Yes | PASS | Repository / Scene List | Scene asset removed; stale disabled Scene List entry detected after initial commit and removed in 6416ca107509
QA-S07-008 | S0.7 | Build Profiles | Global Scene List order is Bootstrap, MainMenu, Store, TestLab | P0 | Manual | No | PASS | Evidence/S0.7_SceneList.png | Final global order verified: Bootstrap, MainMenu, Store, TestLab
QA-S07-009 | S0.7 | Build Profiles | All four global Scene List entries are enabled | P0 | Manual | No | PASS | Evidence/S0.7_SceneList.png | Developer-confirmed; repository and Scene List audited
QA-S07-010 | S0.7 | Play Mode | Each scene enters and exits Play Mode without red errors | P0 | Manual | No | PASS | Evidence/S0.7_ConsoleClean.png | Developer-confirmed; repository and Scene List audited
QA-S07-011 | S0.7 | Persistence | Scene List and scene assets survive Unity restart | P0 | Manual | No | PASS | Developer validation | Developer-confirmed; repository and Scene List audited
QA-S07-012 | S0.7 | Repository | Commit and push leave GitHub Desktop clean | P0 | Manual | No | PASS | Commits 72af6f82cc44; 6416ca107509 | Developer-confirmed; repository and Scene List audited
QA-S08-001 | S0.8 | Compilation | Three smoke-test scripts import and compile without errors | P0 | Manual | No | PASS | Evidence/S0.8_TestScripts.png | Developer-confirmed; commit 04264a362e33
QA-S08-002 | S0.8 | Test discovery | Test Runner discovers exactly five EditMode tests | P0 | Manual | No | PASS | Evidence/S0.8_EditMode_Pass.png | Developer-confirmed; commit 04264a362e33
QA-S08-003 | S0.8 | Assemblies | Production Assembly Definition dependency graph smoke test passes | P0 | Automated | Yes | PASS | Test Runner | Developer-confirmed; commit 04264a362e33
QA-S08-004 | S0.8 | Assemblies | Test Assembly Definition platform and reference smoke test passes | P0 | Automated | Yes | PASS | Test Runner | Developer-confirmed; commit 04264a362e33
QA-S08-005 | S0.8 | Scenes | Scene assets, global Scene List and build indexes smoke tests pass | P0 | Automated | Yes | PASS | Test Runner | Developer-confirmed; commit 04264a362e33
QA-S08-006 | S0.8 | EditMode | Complete EditMode suite returns 5 PASS and 0 FAIL | P0 | Manual | No | PASS | Evidence/S0.8_EditMode_Pass.png | Developer-confirmed; commit 04264a362e33
QA-S08-007 | S0.8 | Test discovery | Test Runner discovers exactly four PlayMode tests | P0 | Manual | No | PASS | Evidence/S0.8_PlayMode_Pass.png | Developer-confirmed; commit 04264a362e33
QA-S08-008 | S0.8 | PlayMode | Bootstrap loads and contains zero root GameObjects | P0 | Automated | Yes | PASS | Test Runner | Developer-confirmed; commit 04264a362e33
QA-S08-009 | S0.8 | PlayMode | MainMenu, Store and TestLab load with approved camera/light roots | P0 | Automated | Yes | PASS | Test Runner | Developer-confirmed; commit 04264a362e33
QA-S08-010 | S0.8 | Regression | All nine tests pass again after Unity restart with a clean Console | P0 | Manual | No | PASS | Evidence/S0.8_ConsoleClean.png | Developer-confirmed; commit 04264a362e33
QA-S09-001 | S0.9 | Build Profile | Tracked Windows_Development profile exists and is active | P0 | Manual | No | PASS | Assets/_Project/Settings/BuildProfiles/Windows_Development.asset | Profile asset audited in commit e1998dffe52d
QA-S09-002 | S0.9 | Scenes | Effective build Scene List contains the four approved scenes in order | P0 | Manual | No | PASS WITH OBSERVATION | Windows_Development asset; commit e1998dffe52d | Profile inherits the approved global list; profile-specific override deferred to S0.10
QA-S09-003 | S0.9 | Windows | Architecture is Intel 64-bit and target is Local Machine | P0 | Manual | No | PASS | Evidence/S0.9_BuildProfile.png | Developer-confirmed; commit e1998dffe52d
QA-S09-004 | S0.9 | Build Options | Development Build and LZ4 are enabled with debugging extras disabled | P0 | Manual | No | PASS | Evidence/S0.9_BuildProfile.png | Developer-confirmed; commit e1998dffe52d
QA-S09-005 | S0.9 | Player Settings | Mono, Use Player Log, Linear, company, product and version are correct | P0 | Manual | No | PASS | Evidence/S0.9_BuildProfile.png | Developer-confirmed; commit e1998dffe52d
QA-S09-006 | S0.9 | Build | Unity completes the Windows build successfully | P0 | Manual | No | PASS | Evidence/S0.9_BuildSuccess.png | Developer-confirmed; commit e1998dffe52d
QA-S09-007 | S0.9 | Build Output | Executable, Data folder, UnityPlayer and crash handler exist | P0 | Manual | No | PASS | Evidence/S0.9_BuildOutput.png | Developer-confirmed; commit e1998dffe52d
QA-S09-008 | S0.9 | Runtime | Player launches outside Unity and remains stable for 10 seconds | P0 | Manual | No | PASS | Evidence/S0.9_PlayerRunning.png | Developer-confirmed; commit e1998dffe52d
QA-S09-009 | S0.9 | Runtime | Player closes cleanly with Alt+F4 and no crash dialog | P0 | Manual | No | PASS | Evidence/S0.9_PlayerRunning.png | Developer-confirmed; commit e1998dffe52d
QA-S09-010 | S0.9 | Logging | Player.log exists and contains no crash or unhandled exception | P0 | Review | No | PASS | Evidence/S0.9_PlayerLog.png | Developer-confirmed; commit e1998dffe52d
QA-S09-011 | S0.9 | Artifact | Build archive SHA-256 is recorded | P1 | Manual | No | PASS WITH OBSERVATION | S0.9 build record | SHA-256 recorded; folder and ZIP sizes not supplied
QA-S09-012 | S0.9 | Repository | Builds is ignored while profile, documentation and evidence are tracked | P0 | Manual | No | PASS | GitHub Desktop | Developer-confirmed; commit e1998dffe52d
QA-S10-001 | S0.10 | Environment | DevelopmentEnvironment_Record contains all required local fields | P1 | Review | No | PASS | DevelopmentEnvironment_Record.md | Developer-confirmed during final S0.10 validation
QA-S10-002 | S0.10 | Player Settings | Standalone Application Identifier equals com.vrmgames.cartridgeandcloud | P0 | Review | Yes | PASS | ProjectSettings/ProjectSettings.asset | Developer-confirmed during final S0.10 validation
QA-S10-003 | S0.10 | Build Profile | Windows_Development owns the approved four-scene list | P0 | Review | Yes | PASS | Windows_Development.asset | Developer-confirmed during final S0.10 validation
QA-S10-004 | S0.10 | Packages | Every optional package has a Keep or Remove decision | P0 | Review | No | PASS | S0.10_Package_Review_Record.md | Developer-confirmed during final S0.10 validation
QA-S10-005 | S0.10 | Packages | Any approved package removal passes compilation and 9/9 regression | P0 | Manual | No | PASS | Test Runner evidence | Developer-confirmed during final S0.10 validation
QA-S10-006 | S0.10 | Cleanup | Assets/Resources.meta is removed or explicitly justified | P1 | Review | Yes | PASS | Repository diff | Developer-confirmed during final S0.10 validation
QA-S10-007 | S0.10 | Regression | Final EditMode and PlayMode suites pass twice | P0 | Manual | No | PASS | S0.10 evidence | Developer-confirmed during final S0.10 validation
QA-S10-008 | S0.10 | Build | Sprint 0 Build002 succeeds and runs outside the Editor | P0 | Manual | No | PASS | Build002 evidence | Developer-confirmed during final S0.10 validation
QA-S10-009 | S0.10 | Artifact | Build002 duration, sizes and SHA-256 are recorded | P1 | Manual | No | PASS | S0.10_Windows_Final_Build_Record.md | 74 seconds; 157 MB (165,653,511 bytes); 65.6 MB (68,875,051 bytes); SHA-256 897d85a00e5afd3d3d019ebf646f2128fa9a27e3bcfa8c50ec3e4ee56c3a2ad6
QA-S10-010 | S0.10 | Repository | Final commit is clean and official baseline remains immutable | P0 | Review | Yes | PASS | GitHub Desktop / main | Commit 478794017015 published; no local changes

## Test_Runs
Run ID | Date | Block | Environment | Scope | Result | Executed by | Evidence / Notes
RUN-S0-001 | 2026-06-21 | S0.1 | Unity 6000.3.18f1 / Windows | Toolchain and editor version | PASS | Blas Luis Rocha González | Two screenshots stored in Evidence
RUN-S0-002 | 2026-06-21 | S0.2 | Unity 6000.3.18f1 / URP | Project settings, URP and clean console | PASS | Blas Luis Rocha González | Developer-confirmed manual run
RUN-S0-003 | 2026-06-21 | S0.3 | Unity Package Manager | Required package baseline | PASS WITH OBSERVATION | Blas Luis Rocha González | Unused template packages remain for review
RUN-S0-004 | 2026-06-21 | S0.4 | GitHub Desktop / main | Ignore rules and clean repository state | PASS | Blas Luis Rocha González | Unity open/close produced no changes
RUN-S0-005 | 2026-06-21 | S0.5 | Unity / repository | Project and documentation structure | PASS | Blas Luis Rocha González | User confirmed all DoD items
RUN-S0-006 | 2026-06-21 | S0.6 | Unity / Test Runner | Assembly graph and compilation | PASS | Blas Luis Rocha González | User confirmed no errors
RUN-S0D-001 | 2026-06-21 | S0.6D | Repository / office suite | Documentation tracking sync | PASS | Blas Luis Rocha González | Commit 31a77be; developer confirmed
RUN-S07-001 | 2026-06-22 | S0.7 | Unity 6000.3.18f1 / Windows | Scene baseline, global Scene List and clean Play Mode | PASS | Blas Luis Rocha González | Scene baseline commit 72af6f82cc44; stale Scene List entry fixed in 6416ca107509; developer confirmed clean restart and repository state
RUN-S08-001 | 2026-06-22 | S0.8 | Unity 6000.3.18f1 / Test Framework 1.6.0 | Five EditMode and four PlayMode smoke tests | PASS | Blas Luis Rocha González | 9/9 confirmed and published in 04264a362e33
RUN-S09-001 | 2026-06-22 | S0.9 | Unity 6000.3.18f1 / Windows x64 | Development build, external launch, Player.log and post-fix 9/9 regression | PASS WITH OBSERVATION | Blas Luis Rocha González | Build succeeded in 73.593 s; commit e1998dffe52d; SHA-256 55e50d174b7d…
RUN-S10-001 | 2026-06-22 | S0.10 | Unity 6000.3.18f1 / Windows x64 | Final configuration, package resolution, pre/post-build 9/9 and Build002 | PASS | Blas Luis Rocha González | Build002 74 seconds; external PASS; Player.log clean; 897d85a00e5afd3d…

## Issues
Issue ID | Block | Severity | Area | Description | Recommended action | Status | Target
ISS-S0-001 | S0.1 | Low | Documentation | DevelopmentEnvironment_Record remains incomplete | Resolved by baseline v0.4 consolidation | Closed | S0.10
ISS-S0-002 | S0.3 | Medium | Packages | Template includes Collab Proxy, Multiplayer Center and Visual Scripting | Resolved by baseline v0.4 consolidation | Closed | Before S0.7 or S0.10
ISS-S0-003 | S0.3 | Low | Packages | Timeline is installed without a current requirement | Resolved by baseline v0.4 consolidation | Closed | S0.10
ISS-S0-004 | S0.5 | Medium | Documentation | S0.5 document previously showed pending state | Resolved by S0.6D operational sync | Closed | S0.6D
ISS-S0-005 | S0.6 | Medium | Documentation | S0.6 validation checklist was previously unchecked | Resolved by S0.6D operational sync | Closed | S0.6D
ISS-S0-006 | S0.6D | High | Governance | Operational Excel and traceability were absent | Resolved by commit 31a77be | Closed | S0.6D
ISS-S07-001 | S0.7 | High | Build | Initial Scene List retained a disabled stale SampleScene reference | Removed through Build Profiles and published in 6416ca107509 | Closed | S0.7
ISS-S07-002 | S0.7 | Medium | Repository | Scene or meta files could be copied outside Unity | Scenes and Unity-generated metadata published in 72af6f82cc44 | Closed | S0.7
ISS-S08-001 | S0.8 | High | Testing | Smoke-test compilation, discovery or execution can fail | Resolved by 9/9 PASS and commit 04264a362e33 | Closed | S0.8
ISS-S09-001 | S0.9 | High | Build | First external Windows player was built and run | Resolved by commit e1998dffe52d | Closed | S0.9
ISS-S09-002 | S0.9 | High | Build | First build failed because PlayMode tests were compiled into the Player | Add UNITY_INCLUDE_TESTS to the PlayMode asmdef and rerun tests/build | Closed | S0.9
ISS-S09-003 | S0.9 | Low | Build Profile | Windows_Development inherits the global Scene List | Resolved by baseline v0.4 consolidation | Closed | S0.10
ISS-S09-004 | S0.9 | Low | Documentation | Build folder and ZIP sizes were not recorded | Record all sizes for Build002 | Accepted | S0.10
ISS-S09-005 | S0.9 | Low | Evidence | Dedicated Build Profile screenshot was not committed | Use the tracked profile asset as evidence and capture final profile in S0.10 | Accepted | S0.10
ISS-S10-001 | S0.10 | High | Player Settings | Application Identifier still contains Unity template values | Resolved and validated in S0.10 | Closed | S0.10
ISS-S10-002 | S0.10 | Medium | Packages | Five nonessential packages still require explicit decisions | Resolved and validated in S0.10 | Closed | S0.10
ISS-S10-003 | S0.10 | Low | Repository | Assets/Resources.meta has no documented owner or content | Resolved and validated in S0.10 | Closed | S0.10
ISS-S10-004 | S0.10 | High | Validation | Pre-final changes have not yet been compiled or tested in Unity | Resolved and validated in S0.10 | Closed | S0.10
ISS-S10-005 | S0.10 | High | Build | Build002 does not yet exist | Resolved and validated in S0.10 | Closed | S0.10
ISS-S10-006 | S0.10 | Medium | Publication | UTF-8 corruption and stale publication metadata detected after closure commit | Resolved by baseline v0.4 consolidation | Closed | Post-publication

## Evidence
Evidence ID | Block | Type | Path / Reference | Status | Supports
EV-S0-001 | S0.1 | Screenshot | Evidence/S0.1_UnityHub_EditorVersion.png | Available | QA-S0-001
EV-S0-002 | S0.1 | Screenshot | Evidence/S0.1_AboutUnity.png | Available | QA-S0-002
EV-S0-003 | S0.2 | File | ProjectSettings/ProjectVersion.txt | Available | QA-S0-004
EV-S0-004 | S0.3 | File | Packages/manifest.json | Available | QA-S0-010; QA-S0-011; QA-S0-012
EV-S0-005 | S0.3 | File | Packages/packages-lock.json | Available | Package restoration
EV-S0-006 | S0.4 | File | .gitignore | Available | QA-S0-013; QA-S0-014
EV-S0-007 | S0.4 | File | .gitattributes | Available | QA-S0-016
EV-S0-008 | S0.5 | Commit | 1cc30ad69a2c093a8e1e0686451302689eb632bb | Available | QA-S0-018 to QA-S0-021
EV-S0-009 | S0.6 | Commit | 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Available | QA-S0-022 to QA-S0-028
EV-S0D-001 | S0.6D | Commit | 31a77be358a3b8e9268cd69abb02a1f52d429fbd | Available | QA-S0D-001 to QA-S0D-005
EV-S07-001 | S0.7 | Screenshot | Evidence/S0.7_SceneAssets.png | Available | QA-S07-001; QA-S07-002; QA-S07-007
EV-S07-002 | S0.7 | Screenshot | Evidence/S0.7_SceneList.png | Available | QA-S07-008; QA-S07-009
EV-S07-003 | S0.7 | Screenshot | Evidence/S0.7_BootstrapHierarchy.png | Available | QA-S07-003
EV-S07-004 | S0.7 | Screenshot | Evidence/S0.7_MainMenuHierarchy.png | Available | QA-S07-004
EV-S07-005 | S0.7 | Screenshot | Evidence/S0.7_StoreHierarchy.png | Available | QA-S07-005
EV-S07-006 | S0.7 | Screenshot | Evidence/S0.7_TestLabHierarchy.png | Available | QA-S07-006
EV-S07-007 | S0.7 | Screenshot | Evidence/S0.7_ConsoleClean.png | Available | QA-S07-010
EV-S07-008 | S0.7 | Commit | 72af6f82cc4458c716d751f5846075bfe47aa093 | Available | QA-S07-001 to QA-S07-012
EV-S07-009 | S0.7 | Commit | 6416ca107509dd81428575ff9400215022bc7610 | Available | QA-S07-007; QA-S07-008
EV-S08-001 | S0.8 | Screenshot | Evidence/S0.8_TestScripts.png | Available | QA-S08-001
EV-S08-002 | S0.8 | Screenshot | Evidence/S0.8_EditMode_Pass.png | Available | QA-S08-002 to QA-S08-006
EV-S08-003 | S0.8 | Screenshot | Evidence/S0.8_PlayMode_Pass.png | Available | QA-S08-007 to QA-S08-009
EV-S08-004 | S0.8 | Screenshot | Evidence/S0.8_ConsoleClean.png | Available | QA-S08-010
EV-S09-001 | S0.9 | Screenshot | Assets/_Project/Settings/BuildProfiles/Windows_Development.asset | Not provided | QA-S09-001 to QA-S09-005; repository asset substitute
EV-S09-002 | S0.9 | Screenshot | Evidence/S0.9_BuildSuccess.png | Available | QA-S09-006
EV-S09-003 | S0.9 | Screenshot | Evidence/S0.9_BuildOutput.png | Available | QA-S09-007
EV-S09-004 | S0.9 | Screenshot | Evidence/S0.9_PlayerRunning.png | Available | QA-S09-008; QA-S09-009
EV-S09-005 | S0.9 | Screenshot | Evidence/S0.9_PlayerLog.png | Available | QA-S09-010
EV-S09-006 | S0.9 | Screenshot | Evidence/S0.9_ConsoleClean.png | Available | QA-S09-006
EV-S09-007 | S0.9 | Commit | e1998dffe52d0d4191abe3f8bda3b577d84bdb04 | Available | QA-S09-001 to QA-S09-012
EV-S09-008 | S0.9 | SHA-256 | 55e50d174b7de4c33308309824cd3990760f7dc421b98d9ee61fdefd83ff8f6e | Available | QA-S09-011
EV-S10-001 | S0.10 | Report | Documentation/10_Development_Records/Sprints/Sprint_00/S0.10_Applied_Changes_Report.md | Available | QA-S10-001 to QA-S10-006 - consolidated in baseline v0.4
EV-S10-002 | S0.10 | Screenshot | Evidence/S0.10_EditMode_Pass.png | Available | QA-S10-005; QA-S10-007 - consolidated in baseline v0.4
EV-S10-003 | S0.10 | Screenshot | Evidence/S0.10_PlayMode_Pass.png | Available | QA-S10-005; QA-S10-007 - consolidated in baseline v0.4
EV-S10-004 | S0.10 | Build record | Documentation/10_Development_Records/Builds/S0.10_Windows_Final_Build_Record.md | Prepared | QA-S10-008; QA-S10-009
EV-S10-005 | S0.10 | Developer validation | Pre-build and post-build 9/9 confirmation | Available | QA-S10-005; QA-S10-007
EV-S10-006 | S0.10 | Build record | Documentation/10_Development_Records/Builds/S0.10_Windows_Final_Build_Record.md | Available | QA-S10-008; QA-S10-009
EV-S10-007 | S0.10 | SHA-256 | 897d85a00e5afd3d3d019ebf646f2128fa9a27e3bcfa8c50ec3e4ee56c3a2ad6 | Available | QA-S10-009

## Regression_Checklist
Regression ID | Trigger | Check | Priority | Status | Notes
REG-S0-001 | Any package change | Unity opens without package resolution errors | P0 | PASS | Validated during Sprint 0 final package/build regression
REG-S0-002 | Any package change | Console remains free of red errors | P0 | PASS | Validated during Sprint 0 final package/build regression
REG-S0-003 | Any package change | All six asmdefs compile | P0 | PASS | Validated during Sprint 0 final package/build regression
REG-S0-004 | Documentation sync | GitHub Desktop ignores generated Unity files | P0 | PASS | Developer confirmed S0.6D
REG-S0-005 | Documentation sync | Operational workbooks open without repair prompts | P0 | PASS | Developer confirmed S0.6D
REG-S0-006 | Documentation sync | Official baseline files remain unmodified | P0 | PASS | Commit 31a77be only changed Development_Records
REG-S07-001 | Scene creation | All six assemblies continue compiling | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-002 | Scene List change | Unity opens without missing scene references | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-003 | Scene cleanup | URP settings and template assets remain valid | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S07-004 | Commit | GitHub Desktop excludes generated caches | P0 | PASS | Validated during S0.7; commits 72af6f82cc44 / 6416ca107509
REG-S08-001 | Test import | The six existing asmdefs remain unchanged | P0 | PASS | Validated in commit 04264a362e33
REG-S08-002 | EditMode run | Scene assets and global order remain unchanged | P0 | PASS | Validated in commit 04264a362e33
REG-S08-003 | PlayMode run | All scenes load without errors or unexpected roots | P0 | PASS | Validated in commit 04264a362e33
REG-S08-004 | Unity restart | The complete suite passes a second time | P0 | PASS | Validated in commit 04264a362e33
REG-S09-001 | Build profile creation | Global Scene List remains unchanged | P0 | PASS WITH OBSERVATION | Global list remained correct; profile override deferred
REG-S09-002 | Player settings review | Assemblies and nine tests still compile | P0 | PASS | 9/9 confirmed after UNITY_INCLUDE_TESTS
REG-S09-003 | Windows build | Editor Console remains clean | P0 | PASS | BuildSuccess and ConsoleClean evidence published
REG-S09-004 | External launch | Player.log has no crash or unhandled exception | P0 | PASS | PlayerLog evidence and developer confirmation
REG-S09-005 | Commit | Build output remains ignored | P0 | PASS | Commit e1998dffe52d contains no build binaries
REG-S10-001 | Application Identifier change | 9/9 tests remain available and pass | P0 | PASS | Validated during final S0.10 run
REG-S10-002 | Package removal | 9/9 pass after every approved removal | P0 | PASS | Validated during final S0.10 run
REG-S10-003 | Profile Scene List override | Global and profile lists both remain correct | P0 | PASS | Validated during final S0.10 run
REG-S10-004 | Final project restart | Second complete suite returns 9/9 | P0 | PASS | Validated during final S0.10 run
REG-S10-005 | Build002 | Player launches and Player.log is clean | P0 | PASS | Validated during final S0.10 run

## References
Reference | Purpose | URL | Accessed
Unity Test Framework manual | EditMode and PlayMode test execution | https://docs.unity.cn/6000.0/Documentation/Manual/testing-editortestsrunner.html | 2026-06-22
PlayMode tests | PlayMode assembly and execution behavior | https://docs.unity.cn/Packages/com.unity.test-framework@1.4/manual/course/play-mode-tests.html | 2026-06-22
SceneManager.LoadSceneAsync | Asynchronous scene loading used by smoke tests | https://docs.unity3d.com/ScriptReference/SceneManagement.SceneManager.LoadSceneAsync.html | 2026-06-22
Project repository | Implementation baseline | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud | 2026-06-22
Build Profiles | Create versionable profiles and profile-specific scenes | https://docs.unity3d.com/current/Manual/build-profiles.html | 2026-06-22
Windows build settings | Architecture, development build, compression and output files | https://docs.unity3d.com/current/Manual/WindowsStandaloneBinaries.html | 2026-06-22
Standalone Player settings | Mono, Use Player Log and configuration | https://docs.unity3d.com/current/Manual/class-PlayerSettingsStandalone.html | 2026-06-22
Scripting backends | Mono and IL2CPP comparison | https://docs.unity3d.com/current/Manual/scripting-backends-intro.html | 2026-06-22
Log files | Windows Player.log location | https://docs.unity3d.com/current/Manual/log-files.html | 2026-06-22