## Dashboard
Cartridge & Cloud — Change Traceability
Official baseline v0.4 - Sprint 0 traceability closed
KPI | Value | Traceability policy
Change entries | 41 | All Sprint 0 technical and documentation changes are consolidated in official baseline v0.4. The next sprint must create a new operational change set.
Accepted | 41
Pending validation | 0
Documentation updates pending | 0
ADRs accepted | 8
Latest audited commit | v0.0.1-project-foundation

## Change_Log
Change ID | Date | Type | Block | Summary | Files / Scope | Evidence | Status | Debt / Follow-up
CHG-S0-001 | 2026-06-21 | Proceso | S0.1 | Freeze Unity 6.3 LTS 6000.3.18f1 and Windows toolchain | Unity Hub / Editor installation | Evidence/S0.1_UnityHub_EditorVersion.png; Evidence/S0.1_AboutUnity.png | Accepted | Complete environment record before S0.10
CHG-S0-002 | 2026-06-21 | Proceso | S0.2 | Create clean Unity URP project | Assets; Packages; ProjectSettings | Commit 6429c7cff05fb8e77e7161ce72f28fb79d03383f | Accepted | None
CHG-S0-003 | 2026-06-21 | Proceso | S0.3 | Install package baseline and Localization | Packages/manifest.json; Packages/packages-lock.json | Repository main | Accepted | Review unused template packages
CHG-S0-004 | 2026-06-21 | Proceso | S0.4 | Configure GitHub Desktop repository workflow | Repository root; main branch | Commit 6429c7cff05fb8e77e7161ce72f28fb79d03383f | Accepted | None
CHG-S0-005 | 2026-06-21 | Proceso | S0.4 | Update Unity ignore rules and track Visual Studio config | .gitignore; .vsconfig | Commit 46c76312fe3f2e93da48334be4862d019e34019d | Accepted | None
CHG-S0-006 | 2026-06-21 | Proceso | S0.4 | Add repository attributes for Unity text and binary assets | .gitattributes | Commit 3d49ef4fae0ebbe4f5739b58d1ac08c5dd068264 | Accepted | Git LFS deferred
CHG-S0-007 | 2026-06-21 | Proceso | S0.5 | Create Assets/_Project hierarchy | Assets/_Project | Commit 1cc30ad69a2c093a8e1e0686451302689eb632bb | Accepted | None
CHG-S0-008 | 2026-06-21 | Documentación | S0.5 | Integrate official v0.3 documentation baseline | Documentation/00_Official_Baseline/v0.3 | Commit 1cc30ad69a2c093a8e1e0686451302689eb632bb | Accepted | Keep immutable
CHG-S0-009 | 2026-06-21 | Código nuevo | S0.6 | Create Domain, Application, Infrastructure and Presentation asmdefs | Assets/_Project/Scripts | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Accepted | No gameplay code
CHG-S0-010 | 2026-06-21 | Código nuevo | S0.6 | Create EditMode and PlayMode test asmdefs | Assets/_Project/Tests | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Accepted | Tests implemented in S0.8
CHG-S0-011 | 2026-06-21 | Refactor | S0.6 | Remove generic Shared folder and enforce dependency boundaries | Assets/_Project/Scripts/Shared | Commit 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | Accepted | None
CHG-S0-012 | 2026-06-21 | Documentación | S0.6D | Create operational production tracking workbook | Documentation/10_Development_Records/Production_Tracking | Commit 31a77be | Accepted | Superseded by v0.3.2 current operational copy
CHG-S0-013 | 2026-06-21 | Documentación | S0.6D | Create operational QA matrix and test runs | Documentation/10_Development_Records/Production_Tracking | Commit 31a77be | Accepted | Superseded by v0.3.2 current operational copy
CHG-S0-014 | 2026-06-21 | Documentación | S0.6D | Create operational traceability workbook and ADRs | Documentation/10_Development_Records | Commit 31a77be | Accepted | Continue updating at each block
CHG-S0-015 | 2026-06-21 | Documentación | S0.6D | Close S0.5 and S0.6 records with PASS results | Documentation/10_Development_Records/Sprints/Sprint_00 | Commit 31a77be | Accepted | None
CHG-S0-016 | 2026-06-21 | Proceso | S0.6D | Developer confirms S0.6D local validation | Documentation sync and repository state | Developer confirmation | Accepted | None
CHG-S0-017 | 2026-06-21 | Proceso | S0.7 | Freeze scene names, responsibilities and global order | Bootstrap; MainMenu; Store; TestLab | ADR-0005 | Accepted | Scene assets pending
CHG-S0-018 | 2026-06-21 | Documentación | S0.7 | Prepare S0.7 procedure, QA and operational workbook v0.3.2 | Documentation/10_Development_Records | Commit 72af6f82cc4458c716d751f5846075bfe47aa093 | Accepted | Superseded by operational workbooks v0.3.3
CHG-S0-019 | 2026-06-22 | Proceso | S0.7 | Create four scenes, configure exact global order and remove stale SampleScene entry | Assets/_Project/Scenes; ProjectSettings/EditorBuildSettings.asset | Commits 72af6f82cc4458c716d751f5846075bfe47aa093; 6416ca107509dd81428575ff9400215022bc7610 | Accepted | None
CHG-S0-020 | 2026-06-22 | Proceso | S0.8 | Freeze the nine-test smoke baseline and execution policy | ADR-0006 | S0.8 package | Accepted | S0.9 remains blocked until 9/9 PASS
CHG-S0-021 | 2026-06-22 | Código nuevo | S0.8 | Prepare five EditMode and four PlayMode smoke tests | Assets/_Project/Tests | Commit 04264a362e33c6b823a51f82434b38d879c3dae1 | Accepted | None
CHG-S0-022 | 2026-06-22 | Documentación | S0.8 | Prepare S0.8 procedure, checklist and operational workbooks v0.3.4 | Documentation/10_Development_Records | Commit 04264a362e33c6b823a51f82434b38d879c3dae1 | Accepted | None
CHG-S0-023 | 2026-06-22 | Proceso | S0.8 | Developer confirms nine smoke tests and clean Console | Assets/_Project/Tests; Evidence/S0.8_* | Commit 04264a362e33c6b823a51f82434b38d879c3dae1 | Accepted | None
CHG-S0-024 | 2026-06-22 | Proceso | S0.9 | Freeze Windows x64 Development Build baseline | ADR-0007 | S0.9 package | Accepted | Release backend and profile deferred
CHG-S0-025 | 2026-06-22 | Documentación | S0.9 | Prepare build procedure, checklist, record and operational v0.3.5 | Documentation/10_Development_Records | Commit e1998dffe52d0d4191abe3f8bda3b577d84bdb04 | Accepted | Superseded by v0.3.6 closure tracking
CHG-S0-026 | 2026-06-22 | Proceso | S0.9 | Create tracked Build Profile and first external Windows player | Assets/_Project/Settings/BuildProfiles; Builds/Windows | Commit e1998dffe52d0d4191abe3f8bda3b577d84bdb04 | Accepted | Superseded by v0.3.6 closure tracking
CHG-S0-027 | 2026-06-22 | Corrección | S0.9 | Exclude PlayMode tests from normal Player compilation | Assets/_Project/Tests/PlayMode/VRMGames.CartridgeAndCloud.Tests.PlayMode.asmdef | Commit e1998dffe52d0d4191abe3f8bda3b577d84bdb04 | Accepted | UNITY_INCLUDE_TESTS preserves Test Runner and fixes Player build
CHG-S0-028 | 2026-06-22 | Proceso | S0.9 | Build and execute first Windows x64 Development Player | Builds/Windows/Development/CAC_v0.0.1_Sprint0_Dev_Windows_x64_2026-06-22_Build001 | Commit e1998dffe52d0d4191abe3f8bda3b577d84bdb04; SHA-256 55e50d174b7de4c33308309824cd3990760f7dc421b98d9ee61fdefd83ff8f6e | Accepted | Sizes not recorded; profile inherits global Scene List
CHG-S0-029 | 2026-06-22 | Documentación | S0.9 | Close Build Record and validation checklist with actual results | Documentation/10_Development_Records | S0.9 closure package | Accepted | Consolidated in official baseline v0.4
CHG-S0-030 | 2026-06-22 | Proceso | S0.10 | Freeze Sprint 0 foundation closure criteria | ADR-0008 | S0.10 preparation package | Accepted | Tag blocked until final PASS
CHG-S0-031 | 2026-06-22 | Configuración | S0.10 | Prepare canonical application identifiers | ProjectSettings/ProjectSettings.asset | S0.10 pre-final script | Accepted | Validated by tests and Build002
CHG-S0-032 | 2026-06-22 | Configuración | S0.10 | Prepare profile-specific four-scene list | Assets/_Project/Settings/BuildProfiles/Windows_Development.asset | S0.10 pre-final script | Accepted | Validated by tests and Build002
CHG-S0-033 | 2026-06-22 | Paquetes | S0.10 | Remove five nonessential direct dependencies | Packages/manifest.json; Packages/packages-lock.json | S0.10 pre-final script | Accepted | Validated by tests and Build002
CHG-S0-034 | 2026-06-22 | Corrección | S0.10 | Remove orphan Resources metadata when empty | Assets/Resources.meta | S0.10 pre-final script | Accepted | Validated by tests and Build002
CHG-S0-035 | 2026-06-22 | Documentación | S0.10 | Prepare environment capture, Build002 record and operational v0.3.7 | Documentation/10_Development_Records | S0.10 pre-final package | Accepted | Build results remain pending
CHG-S0-036 | 2026-06-22 | QA | S0.10 | Run final 9/9 suite before Build002 | Assets/_Project/Tests | Developer confirmation | Accepted | 5/5 + 4/4
CHG-S0-037 | 2026-06-22 | Build | S0.10 | Create and validate Sprint 0 final Windows build | Builds/Windows/Development/CAC_v0.0.1_Sprint0_Final_Windows_x64_2026-06-22_Build002 | SHA-256 897d85a00e5afd3d3d019ebf646f2128fa9a27e3bcfa8c50ec3e4ee56c3a2ad6 | Accepted | 74 seconds; 157 MB (165,653,511 bytes); 65.6 MB (68,875,051 bytes)
CHG-S0-038 | 2026-06-22 | QA | S0.10 | Run complete 9/9 suite after Build002 | Assets/_Project/Tests | Developer confirmation | Accepted | 5/5 + 4/4
CHG-S0-039 | 2026-06-22 | Documentación | S0.10 | Prepare final closure documents and operational v0.3.8 | Documentation/10_Development_Records | S0.10 final closure package | Accepted | Publication pending
CHG-S0-040 | 2026-06-22 | Publicación | S0.10 | Publish Sprint 0 technical closure | Repository main | Commit 478794017015054571d6ca22332a201589abbe5c | Accepted | Commit and push verified; no local changes
CHG-S0-041 | 2026-06-22 | Documentación | Post-publication | Repair UTF-8 mojibake and consolidate closure metadata | Environment, Sprint 00 closure docs and operational workbooks | Post-publication fix package | Accepted | Consolidated in official baseline v0.4

## Decision_Log
ADR | Date | Decision | Status | Drivers | Consequences | Supersedes
ADR-0001 | 2026-06-21 | Use Unity 6.3 LTS 6000.3.18f1, URP and resolved Released packages | Accepted | Stability; LTS support; solo development | Package upgrades require explicit validation | Historical generic Unity 6 LTS wording
ADR-0002 | 2026-06-21 | Use GitHub Desktop on main for the solo workflow | Accepted | Developer familiarity; low process overhead | No command-line Git requirement for normal work | PowerShell-first workflow
ADR-0003 | 2026-06-21 | Keep official baseline immutable and maintain operational copies | Accepted | Auditability; preserve source evidence | Tracking files live in Development_Records | Silent edits to baseline v0.3
ADR-0004 | 2026-06-21 | Use four production assemblies and two test assemblies | Accepted | Separation of concerns; testability | Domain and Application cannot reference Unity | Manager-centric legacy architecture
ADR-0005 | 2026-06-21 | Use Bootstrap, MainMenu, Store and TestLab with fixed global order 0–3 | Accepted | Stable startup, menu, vertical slice and test isolation | Scene names are frozen; future distribution profile excludes TestLab | Historical StorePrototype / StoreSandbox naming
ADR-0006 | 2026-06-22 | Use five EditMode and four PlayMode tests as the Sprint 0 smoke baseline | Accepted | Regression protection without implementing gameplay | S0.9 requires two clean 9/9 executions | Ad hoc manual-only verification
ADR-0007 | 2026-06-22 | Use Windows Intel 64-bit, Mono, Development Build and LZ4 in a tracked profile | Accepted | Fast reproducible first player build; PC/Steam target | S0.9 validates runtime startup; release profile remains separate | Unspecified Windows build configuration
ADR-0008 | 2026-06-22 | Close Sprint 0 only after final environment, package, identifier, profile, test and build audit | Accepted | Reproducible foundation and explicit debt ownership | Foundation tag is blocked until S0.10 PASS | Informal closure without final audit

## Document_Update_Matrix
Document / Workbook | Location | Current state | Required update | Owner | Status | Target block
Official v0.3 baseline | Documentation/00_Official_Baseline/v0.3 | Immutable source | No direct edits | VRM Games | No change | Continuous
S0.5 Project and Documentation Structure | Documentation/10_Development_Records/Sprints/Sprint_00/S0.5_Project_and_Documentation_Structure.md | Closed PASS | No update required | VRM Games | Complete | S0.6D
S0.6 Assembly Definitions | Documentation/10_Development_Records/Sprints/Sprint_00/S0.6_Assembly_Definitions.md | Closed PASS | No update required | VRM Games | Complete | S0.6D
S0.6 Validation Checklist | Documentation/10_Development_Records/Sprints/Sprint_00/S0.6_Validation_Checklist.md | Completed PASS | No update required | VRM Games | Complete | S0.6D
Production operational workbook | Documentation/10_Development_Records/Production_Tracking/Cartridge_And_Cloud_Production_Tracking_Operational_v0.3.8.xlsx | Final pre-publication version | Publish with final commit | VRM Games | Complete | S0.10
QA operational workbook | Documentation/10_Development_Records/Production_Tracking/Cartridge_And_Cloud_QA_Operational_v0.3.8.xlsx | Final pre-publication version | Publish with final commit | VRM Games | Complete | S0.10
Traceability operational workbook | Documentation/10_Development_Records/Production_Tracking/Cartridge_And_Cloud_Traceability_Operational_v0.3.8.xlsx | Final pre-publication version | Publish with final commit | VRM Games | Complete | S0.10
Project Binder / Master Index | Official baseline source | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Unity Project Setup Guide | Official baseline source | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
TDD | Official baseline source | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Build & Versioning Guide | Official baseline source | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
ADR-0005 Scene Baseline | Documentation/10_Development_Records/ADR/ADR-0005-Scene-Baseline-and-Build-Order.md | Closed / current | No update required | VRM Games | Complete | S0.7
S0.7 Scene Baseline | Documentation/10_Development_Records/Sprints/Sprint_00/S0.7_Scene_Baseline.md | Closed / current | No update required | VRM Games | Complete | S0.7
Sprint 00 Current Status | Documentation/10_Development_Records/Sprints/Sprint_00/Sprint_00_Current_Status.md | Closed / current | No update required | VRM Games | Complete | S0.7
ADR-0006 Smoke Test Baseline | Documentation/10_Development_Records/ADR/ADR-0006-Smoke-Test-Baseline-and-Execution-Policy.md | Closed / current | No update required | VRM Games | Complete | S0.8
S0.8 Smoke Tests | Documentation/10_Development_Records/Sprints/Sprint_00/S0.8_Smoke_Tests.md | Closed / current | No update required | VRM Games | Complete | S0.8
S0.8 Validation Checklist | Documentation/10_Development_Records/Sprints/Sprint_00/S0.8_Validation_Checklist.md | Closed / current | No update required | VRM Games | Complete | S0.8
ADR-0007 Windows Build Baseline | Documentation/10_Development_Records/ADR/ADR-0007-Windows-Development-Build-Baseline.md | Closed / current | Replace with closure version where applicable | VRM Games | Complete | S0.9
S0.9 Windows Development Build | Documentation/10_Development_Records/Sprints/Sprint_00/S0.9_Windows_Development_Build.md | Closed / current | Replace with closure version where applicable | VRM Games | Complete | S0.9
S0.9 Validation Checklist | Documentation/10_Development_Records/Sprints/Sprint_00/S0.9_Validation_Checklist.md | Closed / current | Replace with closure version where applicable | VRM Games | Complete | S0.9
S0.9 Build Record | Documentation/10_Development_Records/Builds/S0.9_Windows_Development_Build_Record.md | Closed / current | Replace with closure version where applicable | VRM Games | Complete | S0.9
ADR-0008 Sprint 0 Closure | Documentation/10_Development_Records/ADR/ADR-0008-Sprint-0-Foundation-Closure-Policy.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Development Environment Record | Documentation/10_Development_Records/Environment/DevelopmentEnvironment_Record.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Package Review Record | Documentation/10_Development_Records/Packages/S0.10_Package_Review_Record.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
S0.10 Sprint Closure | Documentation/10_Development_Records/Sprints/Sprint_00/S0.10_Sprint_Closure.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
S0.10 Validation Checklist | Documentation/10_Development_Records/Sprints/Sprint_00/S0.10_Validation_Checklist.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Sprint 00 Foundation Baseline | Documentation/10_Development_Records/Sprints/Sprint_00/Sprint_00_Foundation_Baseline.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
S0.10 Final Build Record | Documentation/10_Development_Records/Builds/S0.10_Windows_Final_Build_Record.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
S0.10 Applied Changes Report | Documentation/10_Development_Records/Sprints/Sprint_00/S0.10_Applied_Changes_Report.md | Validated / current | Publish with final commit | VRM Games | Complete | S0.10
Sprint 00 Closure Record | Documentation/10_Development_Records/Sprints/Sprint_00/Sprint_00_Closure_Record.md | Prepared | Publish with final commit | VRM Games | Complete | S0.10

## Commit_Register
Order | SHA | Message | Scope | Repository URL
1 | 6429c7cff05fb8e77e7161ce72f28fb79d03383f | chore: initialize Unity 6.3 project | S0.1–S0.2 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/6429c7cff05fb8e77e7161ce72f28fb79d03383f
2 | 46c76312fe3f2e93da48334be4862d019e34019d | chore: update Unity gitignore and track Visual Studio config | S0.4 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/46c76312fe3f2e93da48334be4862d019e34019d
3 | 3d49ef4fae0ebbe4f5739b58d1ac08c5dd068264 | chore: add Unity repository attributes | S0.4 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/3d49ef4fae0ebbe4f5739b58d1ac08c5dd068264
4 | 1cc30ad69a2c093a8e1e0686451302689eb632bb | chore: establish project and documentation structure | S0.5 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/1cc30ad69a2c093a8e1e0686451302689eb632bb
5 | 7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9 | chore: establish assembly dependency boundaries | S0.6 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/7f32381d94af98f283fa0cb26b4cbf5b0ba84fe9
6 | 31a77be358a3b8e9268cd69abb02a1f52d429fbd | docs: synchronize Sprint 0 production tracking | S0.6D | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/31a77be358a3b8e9268cd69abb02a1f52d429fbd
7 | 72af6f82cc4458c716d751f5846075bfe47aa093 | chore: establish scene baseline | S0.7 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/72af6f82cc4458c716d751f5846075bfe47aa093
8 | 6416ca107509dd81428575ff9400215022bc7610 | fix: remove stale SampleScene build entry | S0.7 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/6416ca107509dd81428575ff9400215022bc7610
9 | e67555b4f5d6e6cc3d5564fc10573a92b2f80cf2 | docs: close S0.7 scene baseline | S0.7 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/e67555b4f5d6e6cc3d5564fc10573a92b2f80cf2
10 | 04264a362e33c6b823a51f82434b38d879c3dae1 | test: add Sprint 0 smoke-test baseline | S0.8 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/04264a362e33c6b823a51f82434b38d879c3dae1
11 | e1998dffe52d0d4191abe3f8bda3b577d84bdb04 | build: add first Windows development build profile | S0.9 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/e1998dffe52d0d4191abe3f8bda3b577d84bdb04
12 | 69493d5da35873258395808ed9cf9e196f182cd8 | docs: close S0.9 and prepare Sprint 0 closure | S0.9 / S0.10 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/69493d5da35873258395808ed9cf9e196f182cd8
13 | 478794017015054571d6ca22332a201589abbe5c | chore: close Sprint 0 project foundation | S0.10 | https://github.com/BLRochaGonzalez93/U012_CartridgeAndCloud/commit/478794017015054571d6ca22332a201589abbe5c

## Allowed_Types
Allowed change types
Código nuevo
Refactor
Fix
Incidencia / Fix
Documentación
Herramienta Editor
Gameplay / Fórmula
Guardado / Carga
Ajuste visual
Proceso