## Dashboard
Cartridge & Cloud - Excel Maestro de Producción v0.6
KPI | Valor |  | Validación | Estado | Control de fuente | Referencia
Baseline documental | v0.6 |  | EditMode | 1215 PASS | Commit validado | 091090c43855...
Versión aplicación | 0.0.17 |  | PlayMode | 70 PASS | Main observado | d54316c771aa...
Sprints cerrados | 16 |  | Visual Store | FAIL / Open | Working copy | Cambios locales posteriores
Sprint actual | S16 - In Progress |  | Golden Path post-scene | Pending | Baseline | Documentation/.../v0.6
Sprint restante | S17 |  | Build post-scene | Pending | Próximo gate | StoreInitial
Resumen de Sprint
Estado | Cantidad | Notas
Closed / Pass | 16 | S0-S15
In Progress | 1 | S16
Pending | 1 | S17

## Sprint Plan
Sprint | Nombre | Estado | Versión | Entregable / Observación
0 | Project Foundation | Closed / Pass | 0.0.1 | Foundation y build
1 | Bootstrap & Scene Flow | Closed / Pass | 0.0.2 | ApplicationRoot y navegación
2 | Core Data & Save Skeleton | Closed / Pass | 0.0.3 | Sesión y slots
3 | Player Movement & Camera | Closed / Pass | 0.0.4 | Input, movimiento, cámara
4 | Grid & Placement Foundation | Closed / Pass | 0.0.5 | Grid y placement
5 | Store Shell & Access | Closed / Pass | 0.0.6 | Store 10x15 y acceso
6 | Product & Inventory Core | Closed / Pass | 0.0.7 | Inventario
7 | Supplier Orders & Receiving | Closed / Pass | 0.0.8 | Pedidos y recepción
8 | Displays & Restocking | Closed / Pass | 0.0.9 | Displays
9 | Customer Profiles & Spawning | Closed / Pass | 0.0.10 | Clientes
10 | Shopping & Reservations | Closed / Pass | 0.0.11 | Shopping
11 | Queue & Checkout | Closed / Pass | 0.0.12 | Checkout
12 | Day Cycle & Closure | Closed / Pass | 0.0.13 | Día
13 | Economy & Reports | Closed / Pass | 0.0.14 | Economía
14 | Save/Load Complete Slice | Closed / Pass | 0.0.15 | Recovery y schema v2
15 | UI/UX Integration | Closed / Pass | 0.0.16 | HUD y Operations
16 | Art & Audio Representative Pass | In Progress | 0.0.17 | StoreInitial pendiente
17 | Vertical Slice Stabilization | Pending | TBD | Balance, rendimiento, QA y build

## S16 Work Packages
Paso | Paquete | Área | Estado | Prioridad | Criterio
1 | Crear StoreInitial.unity | Scene | Not Started | High | Duplicar Store funcional; smoke test
2 | Crear StoreInitialEnvironment.prefab | Art/Scene | Not Started | High | Solo entorno y técnicos
3 | Montar suelo y arquitectura | Art/Scene | Not Started | Critical | 10x15, muros, fachada
4 | Configurar puerta | Runtime/Scene | Not Started | Critical | Hojas explícitas y posiciones
5 | Colocar mobiliario inicial | Scene | Not Started | Critical | Warehouse/checkout/receiving
6 | Añadir anchors y roots | Scene | Not Started | High | Spawn, zones, dynamic roots
7 | Crear StoreInitialSceneContext | Code | Not Started | Critical | Referencias serializadas
8 | Conectar runtime | Code | Not Started | Critical | Registro y save/load
9 | Desactivar shell procedural | Code | Not Started | Critical | Feature flag y no duplicados
10 | Bloquear clic UI | Code | Not Started | High | EventSystem guard
11 | Validar y construir | QA | Not Started | Critical | Tests, Golden Path, build

## Risks
ID | Riesgo | Impacto | Probabilidad | Estado | Mitigación
R-016-01 | Arquitectura manual no coincide con grid | High | High | Open | Usar PlacementSurface como referencia; QA bounds
R-016-02 | Duplicación procedural + escena | High | High | Open | Feature flag y test de un único shell
R-016-03 | Mobiliario inicial se guarda como dinámico | High | Medium | Open | Registro separado inicial/dinámico
R-016-04 | Puerta pierde funcionalidad | High | Medium | Open | Referencias explícitas y PlayMode test
R-016-05 | Scene list rompe flujo | High | Medium | Open | Cambiar Build Profiles al final
R-016-06 | Input UI sigue propagándose | Medium | High | Open | EventSystem guard + test

## Decisions
ID | Decisión | Estado | Sprint | Racional
ADR-0034 | Runtime registry owns representative catalog reference | Accepted | S16 | Evita lookup incidental en memoria
ADR-0035 | Author StoreInitial manually | Accepted / Implementing | S16 | Reemplaza inferencia procedural visual
DEC-016-01 | Keep procedural fallback until QA | Active | S16 | Rollback seguro
DEC-016-02 | Do not reimport FBX for scene transforms | Active | S16 | Transforms belong to scene authoring
DEC-016-03 | UI click must be consumed before world raycast | Planned | S16 | Fix input propagation