## Dashboard
Cartridge & Cloud - QA Testing Matrix v0.6
Métrica | Valor | Estado | Gate | Obligatorio | Estado
EditMode | 1215 | PASS | Compile clean | Sí | PASS
PlayMode | 70 | PASS | Full automated | Sí | PASS
Total | 1285 | PASS | Store visual | Sí | OPEN
Manual visual Store | 0 | FAIL / Open | Golden Path | Sí | Pending
Post-scene build | 0 | Pending | External EXE | Sí | Pending

## Automated Suites
ID | Suite | Mode | Expected | Last Result | Notes
QA-AUT-001 | Full EditMode | EditMode | 1215 | PASS | Current working copy
QA-AUT-002 | Full PlayMode | PlayMode | 70 | PASS | Current working copy
QA-AUT-003 | Phase1 PlayMode | PlayMode | 17 | PASS | Representative factory repaired
QA-AUT-004 | Phase1AssetAuthoringTests | EditMode | Suite | PASS | Catalog/prefabs
QA-AUT-005 | Runtime Catalog Link Validation | Editor | Command | PASS/Observed | Prefabs visible

## Manual Scenarios
ID | Scenario | Expected | Result | Severity if fail
QA-MAN-001 | StoreInitial smoke | Scene loads with existing gameplay | Pending | S1
QA-MAN-002 | Architecture perimeter | Walls border placement floor | Pending | S1
QA-MAN-003 | Automatic door | Vertical, opens left/right, passage works | Pending | S1
QA-MAN-004 | Initial warehouse furniture | Appears only at authored position | Pending | S1
QA-MAN-005 | Placement | Place/rotate/remove/persist | Pending | S1
QA-MAN-006 | UI click suppression | Operations click never moves player | Pending | S2
QA-MAN-007 | Customers and checkout | Customer completes purchase | Pending | S1
QA-MAN-008 | Day close/save/reload | Golden Path persists | Pending | S1
QA-MAN-009 | Wall occlusion | Expected walls hide/show | Pending | S2
QA-MAN-010 | Audio/VFX | No missing refs or excessive levels | Pending | S2

## Known Issues
ID | Severity | Issue | State | Resolution
KI-016-01 | S1 | Walls misplaced/scaled | Open | StoreInitial manual authoring
KI-016-02 | S1 | Door orientation and direction | Open | Explicit references/positions
KI-016-03 | S1 | Warehouse shelf wrong location | Open | InitialFurniture root
KI-016-04 | S2 | Operations click moves player | Open | EventSystem guard
KI-016-05 | S2 | Possible duplicate shell | Open | Feature flag/test

## Release Gate
Gate | State | Policy
Compile clean | PASS | Required
EditMode complete | PASS | Required
PlayMode complete | PASS | Required
StoreInitial visual approval | OPEN | Required
Golden Path post-migration | Pending | Required
Windows x64 Development Build | Pending | Required
External EXE / Player.log | Pending | Required
Documentation closure | Pending | Required