## Change Log
ID | Date | Type | Change | State | Impact
CHG-060-001 | 2026-07-01 | Baseline | Publish standalone documentation v0.6 | Documented | All docs
CHG-060-002 | 2026-07-01 | Status | Record S0-S15 closed; S16 open | Documented | Roadmap/Handoff
CHG-060-003 | 2026-07-01 | Technical | Record representative asset integration | Documented | TDD/Art
CHG-060-004 | 2026-07-01 | Decision | Adopt StoreInitial manual scene | Accepted | ADR-0035
CHG-060-005 | 2026-07-01 | Defect | Record UI click propagation | Open | KI-016-04

## Requirements
Requirement | Description | Implementation | Sprint | Evidence | State
VS-001 | Complete store-day loop | Implemented | S6-S15 | Automated + Golden Path pre-art | Validated functional
VS-002 | Representative initial store | In progress | S16 | Manual visual review | Open
VS-003 | Deterministic save/recovery | Implemented | S14 | Automated | Pass
VS-004 | UI does not leak input to world | Defect open | S16 | PlayMode/manual | Open
VS-005 | Windows external build | Pre-art pass; post-art pending | S16/S17 | Build run | Pending

## ADR Register
ADR | Sprint | Decision | Status | Consequence
ADR-0034 | S16 | Runtime registry catalog link | Accepted | Representative catalog deterministic
ADR-0035 | S16 | Manual StoreInitial scene | Accepted / Implementing | Replace procedural visual inference

## Document Register
Document | Version | State | Area
Guide | v0.6 | Current | Governance
Enfoque | v0.8 | Current | Governance
GDD | v0.6 | Current | Design
Vertical Slice Specification | v0.4 | Current | Design
TDD | v0.6 | Current | Technical
Data Model | v0.5 | Current | Technical
Roadmap | v0.6 | Current | Production
QA Plan | v0.6 | Current | QA
Art Bible | v0.5 | Current | Visual
Current Project Handoff | v0.6 | Current | Handoff